| Program Name: | California Department of Corrections and Rehabilitation Partnership |
| --- | --- |
| Program Number: | SCG3519 |
| Quarter: | Second Quarter 2007 |

- Program Description:

Southern California Gas Company, The California Department of Corrections & Rehabilitation (CDCR) and the other three Investor Owned Utilities (IOUs) are collaborating on a new Energy Efficiency Partnership program to share energy efficiency best practices and to implement energy efficiency projects for immediate and long-term energy savings and peak demand reduction.

The Department of Corrections is a public institution and has recently merged with the California Youth Authority.  The new organization will be comprised of 34 adult facilities and 16 parole offices.  These facilities will have approximately 37,715,415 square feet of occupied space.  There will be an addition of 8 youth facilities with approximately 10 million square feet and four camp locations.   Through this transition, Southern California Gas Company and the other IOUs, will collaborate with CDCR to develop an implementation plan and schedule that will ensure timely implementation of identified projects and exceed program objectives.

- Administrative Activities:

- CDCR partners are collaborating with the State of California effort, coordinated through State of California partnership, to avoid any overlap in program activities and process.  CDCR will follow the requirements to secure project financing through GS$Mart.  The process requires the development of an engineering package with information evaluated through a life cycle cost analysis model to demonstrate the cost effectiveness of the projects. GS$Mart will fund the projects if they meet or exceed program funding criteria.

- CDCR management released an RFQ to solicit qualification from various vendors to support CDCR project implementation effort.  CDCR was successful in creating a pool of qualified ESCOs and engineering management consultants.

- SCG provided additional engineering assistance with second phase of project assessment.  These activities provided information beyond the existing projects identified by previous site audits that were a few years old.  The engineering consultant completed audits at all CDCR facilities in SCG territory and six reports were submitted to CDCR for review and incorporate into the ESCO process.

- The management team met to discuss the procurement of project management consultant (PMC) services.  The PMC will assist the statewide partnership and CDCR.  A scope of work was finalized that includes coordination and communication with contracted ESCOs and engineering support.  PG&E will procure the PMC services on behalf of the statewide partnership.

- Marketing Activities:

CDCR Facility Management Division has statewide oversight of all facilities.  This includes facilities in all four IOU service territories.  Periodic communications related to partnership implementation activities, especially training opportunities will be disseminated through a pre-established communication infra-structure.  Types of communication to include energy efficiency training information for Prison staff to encourage behavioral changes in conservation and to increase energy efficiency knowledge.

- Direct Implementation Activities:

- SCG collaborated with CDCR representatives to identify facilities that would require preliminary facility assessments.  The assessments will provide CDCR with existing measure information such as types, estimated quantity, energy savings and costs to implement.  CDCR will be able to use the analysis in their contracting discussions with the vendors as well as to support financing requests through GS$Mart

- SCG provided audits through Lincus Engineering for the six facilities noted below. Potential projects were identified with estimated energy savings and incentives.  SCG will work with CDCR to further develop the projects for implementation.

California Institution for Men - Chino

California Institution for Women - Chino

California State Prison - Ironwood

California State Prison - Lancaster

California Rehabilitation Center - Norco

California Rehabilitation Center – North Kern

- Project Agreement Packages are being created based on the audits conducted in May 2007.  This agreement will commit the funds for the projects and allow CDCR to move forward with implementation activities including procurement of additional funds through the state’s GS$mart financing program.  The incentives and savings numbers in the agreement will be modified according to assessment of final implementation proposal to be provided by the ESCOs.

- Program Performance/Program Status:

( Program is on target

⁬ Program is exceeding expectations

⁬ Program is falling short of expectations

- Program Achievements (non-resource programs only):

# Not Applicable

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

None

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

None

- Changes to staffing and staff responsibilities, if any:

None

- Changes to contracts, if any:

None

- Changes to contractors and contractor responsibilities, if any:

Partners are in discussion on a potential solicitation for a program administration and management contractor/consultant.  This contractor/consultant will help the management team in the overall administration of the partnership program. The tasks will typically include meeting and workshop planning, administrative duties, and coordination of special activities including reporting of results to all the partners.  PG&E will be the lead IOU to initiate this effort.

- Number of customer complaints received:

None

- Revisions to program theory and logic model, if any:

None