| Program Name: | Designed for Comfort |
| --- | --- |
| Program Number: | SCG3537 |
| Quarter: | Third Quarter 2007 |

- Program description

Designed for Comfort: Efficient Affordable Housing (referred to as DfC hereafter) is a resource acquisition program that addresses the multifamily affordable housing retrofit market segment.  The program uses a performance-based approach to encourage affordable housing property owners to choose the most cost-effective measures to achieve a 20% energy improvement over existing building conditions.  The program aims to transform the multifamily retrofit market away from a prescriptive, one-size-fits-all approach, toward a comprehensive building analysis approach that uses energy consultants and HERS Raters to evaluate a wide palette of energy efficiency options when rehabilitating multifamily properties.  The program will provide training to tenants on the proper use of their upgraded apartments.  The program will capture opportunities related to behavioral changes that would otherwise be lost, and will also capture some lighting energy savings that the residential Title 24 standards would not.

The DfC program provides long-term energy benefits by promoting a performance-based, comprehensive, cost-effective package of energy efficient measures with long useful lives (typically 16 to 20 years).  These include high performance windows, better insulation, high-efficiency heating, cooling, and water heating equipment, and most likely, a combination of these measures to achieve maximum savings potential.

DfC offers incentives of up to $700/unit (9 or more units), up to $1,500/unit (3-8 units) and up to $500 for special needs housing for qualifying projects.  In all cases, the incentive only covers the costs of the upgrades up to the incremental cost or the incentive amount, whichever is less.

The program activities and accomplishments during the months of April through June 2007 are described below under four broad categories: Administrative, Marketing, Direct implementation and Program Performance and Status.

- Administrative activities

During the 2007 third quarter (July, August and September), HMG conducted the following administrative activities:

Contract change order and revised E3 Calculator: HMG worked with SCG to revise the E3 Calculator, budgets, energy saving and milestone and payment schedule.  HMG also updated the E3 calculator using the most current version.  HMG provided the rationale behind moving marketing funds to administration.  HMG is waiting for the final change order from SCG.

Flat Files:  Flat Files:  HMG scheduled a meeting for July 11, 2007 at SCG to tailor the flat file to the Designed for Comfort program.  HMG had purchased airfare for staff to attend this meeting.  However, the day prior, the meeting was cancelled.  HMG is waiting for SCG/SCE to reschedule this meeting.

Improved Communication: HMG attempted to schedule weekly meetings to improve communications about the program.  However, SCG/SCE representatives have not attended these meetings.  Eventually, HMG cancelled future meetings.

- Marketing Activities

During the 2007 third quarter, HMG did not actively recruit projects, and did not schedule any new participant meetings.  HMG is waiting for cost information and energy savings from projects that are currently enrolled, in order to determine the availability of incentives for additional projects.  Below is a summary of specific marketing activities.

Marketing Materials

All marketing materials were developed prior this quarter.

Marketing Events

HMG’s original marketing strategy was to recruit DfC participants through exhibiting and/or presenting at industry conferences, workshops, and/or meetings.  These venues serve as a direct link to the targeted market. HMG had some marketing events already scheduled for this quarter, prior to the decision to stop direct marketing and outreach.  Following are the details of these events:

Conferences/Seminars

HMG attended SCANPH 2007 in Los Angeles, CA on September 28, 2007, to promote the DfC program.  This conference was attended by over 1,500 professionals in the affordable housing industry, including: developers, advocates, government officials, and service providers.  Project leads obtained from this conference were added to the waitlist.

Meetings

HMG did not schedule any new participant meetings this quarter.

- Direct Implementation Activities

The direct implementation activities include procurement of EnergySmart Paks and the project enrollment process. Both are summarized below.

EnergySmart Paks

In this quarter, HMG purchased and delivered a total of 56 EnergySmart Paks to one project site.

Project Enrollment

HMG has been very successful in recruiting projects both in SCE and SCG areas and is quickly approaching the energy goals set in the recent draft change order. The DfC program currently has seven projects enrolled for incentives with a total of 897 dwelling units.  With these seven projects, HMG expects to reach the kWh savings goal of 281,030, and reach 80% of the Therm savings goal of 56,883.

- Program Performance/Program Status

( Program is on target

⁬ Program is exceeding expectations

⁬ Program is falling short of expectations

The program is currently meeting expectations. Overall, HMG has delivered milestones/deliverables on time, or in advance of program goals.

- Program Changes and Unresolved Issues

HMG has discussed the issue of the new incentive split formula, in that it is impossible for HMG to project the dollar amount of incentives paid to the owner, or how this amount will be divided between utilities until a project is analyzed and plan checked.  This makes it impossible to guarantee an incentive amount to an owner, and very difficult to know when incentive budgets will be depleted for either utility.  When a project signs up for the program, we will not know if there are funds available from the appropriate utility until after the project owner has invested in both an energy consultant and a HERS rater.  This risk may discourage participation and result in a delay of beginning construction on new projects until the projects enrolled are completed.

- Program Achievements (Non-Resource Programs Only):

N/A

- Changes in Program Emphasis, if any, From Previous Quarter

This quarter, HMG and the utilities agreed to stop all marketing and focus on the existing pipeline of projects.  Also, because of anticipated increased administration with managing the incentive funds described in section 6 along with the development of the flat files, marketing effort is now transferred to administration.   The focus is now on finalizing the enrolled projects to see how much incentive funding is left for waitlisted projects.

- Discussion of Near-Term Plans for Program over the Coming Months

In the near-term, HMG plans to focus on getting cost information and projected energy savings for each of the actively enrolled projects, in order to estimate the remaining incentives that may be available for projects currently on the waitlist.

HMG hopes to wrap up all currently enrolled projects by the close of 2007, in order to evaluate remaining incentive funds available for additional project participation.

- Changes to staffing and staff responsibilities, if any

There are no changes in staffing to report.

- Changes to contracts

There are no changes to contracts to report.

- Changes to contractors and contractor responsibilities, if any

There are no changes to contractors to report.

- Number of customer complaints received

There were no customer complaints received in this quarter.

- Revisions to program theory and logic model, if any

There are no revisions to the program theory and logic model.