Program Name:	Mobile/Manufactured Home Innovative Outreach and Measure Program

Program Number:	SCG3539

Quarter:		Fourth Quarter, 2007

- Program Description
The Mobile/Manufactured Home Innovative Outreach and Measure Program has been designed to provide gas measures on a comprehensive basis to 14,500 mobile home customers in the SCG service territory.

- Administrative Activities
We are pleased to report that the third quarter was our strongest quarter of production for the program and also held our two best individual months, which were November and December, with 139,160 Therms saved during the 4th quarter.

We have worked closely with Davi Ibarra and Phillip Jarvey of SCE to strengthen the entire acquisition, installation, inspection and billing process and have successfully built production levels.

Synergy has worked together with SCE-SCG to achieve a high level of accuracy in the data entry process. There are many data points, thus requiring a high level of attention.  We are working with SCE-SCG to develop innovative new systems that completely automate the handling of customer data.

Our business plan is supported by a talented and dedicated marketing and outreach staff, who continue to personally distribute flyers in several parks to increase interest and attendance at follow-up neighborhood meetings.

In an effort to consistently increase production, and therefore hit program targets 6-9 months ahead of schedule, Synergy has worked in conjunction with SCE-SCG to organize the program systems and structures to consistently work through our finding, scheduling, installation and inspection processes. This effort, along with an increase in the number of technicians in the field, has afforded us added production capability.

- Marketing Activities
Our marketing and outreach staff has worked toward supporting our business plan by personally distributing flyers in several parks to increase interest and attendance at follow-up neighborhood meetings. During the fourth quarter, our marketing office sent a total of 45,599 direct mail pieces (15,887 in October; 11,645 in November; 15,067 in December) to mobile home residents in the SCG service area. In addition, our marketing and outreach personnel personally distributed flyers to many mobile home community residents.

Our marketing and outreach personnel have held 56 neighborhood meetings (17 in October; 24 in November; 15 in December) with 1,253 guests in attendance (474 in October; 400 in November; 379 in December) during the fourth quarter. During these meetings a program overview was presented to possible Mobile Home clients. Samples of the measures to be performed were demonstrated and potential clients and program participants were able to ask questions. It was felt that these neighborhood meetings were quite productive. Many customers are able to schedule their appointments for installation directly from these meetings.

Locations and numbers where neighborhood meetings were held are included as follows:

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| October | Cabrillo | Huntington Bch | 5 |
|  | Villa Magnolia | Westminster | 4 |
|  | Town & Country | Santa Ana | 19 |
|  | Kensington Park | Westminster | 88 |
|  | Copacabana MHP | LaVerne | 37 |
|  | Alto Camino MHP | Loma Linda | 20 |
|  | Warren Park | Santa Ana | 21 |
|  | Royal Gardens | Westminster | 112 |
|  | Villa Nova | Pico Rivera | 56 |
|  | Bolsa Verde Estates | Westminster | 7 |
|  | Foothill Vista | Azusa | 51 |
|  | Vista Del Loma | Carson | 5 |
|  | Cherry Field | Paramount | 11 |
|  | Vogue | San Bernardino | 20 |
|  | Highland MHP | San Bernardino | 14 |
|  | Coco MHP | LaVerne | 2 |
|  | Mesa Vista | Orange | 2 |
| Total October | 17 |  | 474 |
| Total PTD | 175 |  | 4,373 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| November | Bloomfield | Cypress | 19 |
|  | Casade Jardine | Bellflower | 14 |
|  | Ramon | Palm Springs | 45 |
|  | Town & Country | Santa Ana | 8 |
|  | University | Loma Linda | 7 |
|  | Bolsa Verde | Westminster | 6 |
|  | Corona Palms | Riverside | 10 |
|  | La Lampara | Stanton | 18 |
|  | Racho Del Sol | Westminster | 19 |
|  | Foothill Vista | Azusa | 1 |
|  | Oxnard Shores | Oxnard | 54 |
|  | Tradewinds | Simi Valley | 15 |
|  | Valecito | Newbury Park | 28 |
|  | Santa Paula West | Santa Paula | 15 |
|  | Thunderbird Oaks | Thousand Oaks | 10 |
|  | Lemonwood | Ventura | 19 |
|  | Santa Paula West | Santa Paula | 15 |
|  | The Ranch | Thousand Oaks | 13 |
|  | Camarillo Springs | Camarillo | 8 |
|  | Heritage MHP | Temecula | 30 |
|  | Friendly Village | La Habra | 27 |
|  | Horizon MHP | Palm Springs | 2 |
|  | Santiago Sunrise Vlge | Palm Springs | 10 |
|  | Rancho Ontario | Ontario | 7 |
| Total November | 24 |  | 400 |
| Total PTD | 199 |  | 4,773 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| December | Lake Park | Santa Ana | 13 |
|  | Lake Park North | Santa Ana | 5 |
|  | Mariners Point | Huntington Beach | 8 |
|  | Saboba | San Jacinto | 35 |
|  | Thunderbird | Garden Grove | 12 |
|  | Lake Park | LaMirada | 50 |
|  | Lake Park | Brea | 34 |
|  | Blue Skies | Santa Barbara | 18 |
|  | Silver Sand | Capinteria | 39 |
|  | Arbor | Capinteria | 28 |
|  | El Dorado | Fillmore | 22 |
|  | Royal Palms | Covina | 41 |
|  | San Vicente | Santa Barbara | 33 |
|  | La Cumbre | Santa Barbara | 16 |
|  | Santa Barbara West | Goleta | 25 |
| Total December | 15 |  | 379 |
| Total PTD | 214 |  | 5,152 |

- Direct Implementation Activities
Synergy continues to monitor ways to improve direct implementation processes and procedures and is pleased that production levels are on track and ahead of schedule.

- Program Performance/Program Status
(	Program is on target
(	Program is exceeding expectations
(	Program is falling short of expectations

- Program Achievements (Non-Resource Programs Only)
Not applicable.  This is a resource program

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measures discontinued, budget changes, etc.).
None, other than we have worked to increase production and complete all work, where possible in 2007.  We are now working with the program management team to explore supplemental funding for 2008 to gain additional energy savings.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.).
Synergy has added additional technicians and crews to increase production throughout the summer months. Not only did these individuals assist during the summer period, but also continued to do so throughout the reminder of 2007 and the fourth quarter.

- Changes to staffing and staff responsibilities, if any.
None

- Changes to contracts, if any.
None

- Changes to contractors and contractor responsibilities, if any.
None

- Number of customer complaints received.
Of the 3,843 customers served in the Mobile Home Program during the fourth quarter of 2007, there were 37 customer complaints, all of which have been successfully resolved to the customers’ satisfaction. A supervisor was sent to each site immediately after each call to diagnose and personally address the issue. We appreciate this feedback and in order to improve our customer service, are working closely with our technicians to make sure that all measures are working properly when leaving the installation site, to use proper business etiquette when on site, to ensure they have the appropriate supplies at each site and we have also worked with the office staff and technicians to address all scheduling concerns, including the timeliness of the technicians for appointments. We are working with the technicians to follow-through carefully with each customer and confirm that each measure is properly functioning before leaving the site and to be more social and communicative.

Synergy received 342 complimentary customer satisfaction calls and cards in the fourth quarter of 2007 and 3,366 program-to-date. Customers are very satisfied with the services rendered and for the program in general.

- Revisions to program theory and logic model, if any.
None. Provided in February 1, 2006 concept paper.